## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://in.ebay.com/
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Dependacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: eBay is an online shopping site that's best known for its auctions and consumer to consumer sales. It's also extremely popular for online merchants to use as a sales channel. eBay's available in many different countries. However, you can search for products available in your local area by entering the zip code. Alternatively, you can search for products available nationally or internationally. FUNCTIONALITY IN THE SCOPE (What Functioanlities to TEST): Inscope: 1)Signing in 1. Once you've opened the Ebay app or Ebay website, select Sign In to access your account and begin buying or selling desired products. the 'Sign In' button directs the user to the 'Sign In' page where the user needs to enter the credentials viz. the registered email or username and its corresponding password. 2. You can sign in on any Ebay-compatible device, or on multiple compatible devices. 3. If the user is a first-time visitor and does not have an account, they have the option to register for the same and avail further services. 2) Continue Using Google Account There is an option of logging in via Google account using which user can login with His/Her Google account. 3) Buy option There is an Buy section which the user can access by click on Buy where the user can select the category of product he/she is looking for. 4)Sell option 1.)Ebay provides an option of selling products which the user is wishing to sell. 2.)When the user clicks on the SELL button, the site is redirected to the SELL page where the user has to decribe their product in brief which they are willing sell. 5)Daily deals 1.)To find out about deals and discounts, the user can click on the DEALS button. 2.) Once redirected to the deals page, the page displays the deals on products which are posted by other users. 6)Help and contact Customer service link is also present if someone doesn't understand what to do next. There are several options like 'Buying as guest' 'get help with an item that hasn't arrived' 'Additional support during COVID-19 for buyers and sellers on eBay' 'Get help with a hacked account' from which you can clear your queries. FUNCTIONALITY OUT of SCOPE (Optional) : Load testing, Localization Testing, Volume Testing Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Stories
Epic | Story ID | Summary | Objective | Acceptance
Signing in | EBAY-29 | Registered User sign in via vaild Email id and Password | Registered User should be able to sign in via Registered Email id and Password to access his/her eBay account | Acceptance1 : Registered User should be able to sign in via Valid Email Id and password. Acceptance 2: Registered User should not be able to sign in via invalid Email Id without @gmail.com or other similar format and click continue it should display a error message “oops, that’s not a match”. Acceptance 3: Registered User should not be able to sign in via valid Email Id and invalid password and should display a error message “oops, that’s not a match”. Acceptance 4: Registered User should not be able to sign in with empty Email id or password input fields and error should be displayed. Acceptance 5: when password is blank, the sign in button is disabled. Note: Any user to login “registration” must have done.
Signing in | EBAY-30 | Sign in page displayed. | Registered User should be displayed the sign in page UI For eBay site | Acceptance1: Registered User should be able to view the predefined input fields for eBay Website sign in page. Acceptance 2: Registered User should be able to view the predefined input fields for eBay App sign in page.
Signing in | EBAY-31 | Registered User can sign in by Google Account / Facebook Account | Registered User should be able to sign in via Google Account / Facebook Account. | Acceptance1: Registered User should be able to sign in by a valid gmail account id and gmail account password. Acceptance 2: Registered User should not be able to sign in via invalid gmail account id without @gmail.com or other similar format and click continue it should display a error message. Acceptance3: Registered User should not be able to sign in via valid gmail account id and invalid gmail account password and should display a error message. Acceptance 4: Registered User should not be able to sign in with empty gmail account id or gmail account password input fields and error should be displayed.

## Test Scenario
Requirement ID | Story Name | Test Scenario | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
EBAY-29 | Enter sign in credentials | TS_Signing in_01 | Verify Sign in with Valid Credentials | Functional | 1 | Check Sign in with valid credentials .
|  |  | Verify Sign in with invalid Credentials | Functional | 3 | Check Sign in with invalid credentials . 1. Check for invalid Email id and valid Password 2. Check for Valid Email id and invalid Password. 3. Check for blank fields.
EBAY-30 | Access through multiple devices | TS_Signing in_02 | Verify that registered user should able to display the sign in page UI For eBay site | UI | 2 | check that registered user should be able to view the predefined input fields for eBay Website sign in page.
check that registered user should be able to view the predefined input fields for eBay App sign in page.
EBAY-31 | Sign in with different accounts. | TS_Signing in_03 | Verify Sign in with Valid Google Account / Facebook Account Credentials | Functional | 1 | check that registered user should be able to sign in by a valid gmail account id and gmail account password.
|  |  | Verify Sign in with invalid Google Account / Facebook Account Credentials | Functional | 2 | check that registered user should not be able to sign in via invalid gmail account id and click continue it should display a error message.
check that registered user should not be able to sign in via valid gmail account id and invalid gmail account password and should display a error message.

## Test Case Template
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
TS_Signing in_01 | Verify that the Sign in page contain elements such as Email id ,Continue button,password,Sign in button. | https://www.ebay.com should be working | To verify Sign in Page | Go to https://www.ebay.com |  | Sign in page contain elements such as Email id, Continue button,Password,Sign in button should be Displayed. | Sign in page contain elements such as Email id, Continue button,Password,Sign in button should be Displayed. | Pass | <Describe the actual test result after execution of test cases second time. In case screenshots need to be attached to substantiate the test result, use the references tab.> | New status of test case after it failed in Iteration 1.
| Verify Sign in with Valid Credentials | 1. eBay site should be working 2. User should have Registered | To verify Sign in page | Go to https://www.ebay.com/ Click Sign in Enter Email Click Continue Enter Password Click Sign in | Valid Email Address,Password | User should be able to Sign in and navigate to eBay main page | User should be able to Sign in and navigate to eBay main page | pass
| Verify Sign in with invalid Credentials | 1. eBay site should be working 2.sign in should be working | To verify invalid Sign in | Go to https://www.ebay.com/ Click Sign in Enter invalid Email Click Continue Enter Password Click Sign in | invalid Email Address | Display message "Opps, that's not a match" | Display message "Opps, that's not a match" | Fail
|  |  |  | Go to https://www.ebay.com/ Click Sign in Enter Email Click Continue Enter invalid Password Click Sign in | invalid Password | Display message "Opps, that's not a match" | Display message "Opps, that's not a match" | Fail
|  |  |  | Go to https://www.ebay.com/ Click Sign in Enter Email Click Continue Enter Password Click Sign in | Leave Email id and passrord blank | Display message "Opps, that's not a match" | Display message "Opps, that's not a match" | Fail
TS_Signing in_02 | Verify that registered user should able to display the sign in page UI For eBay site | eBay app should be installed on the supported mobile devices | To verify Sign in from supported devices | open eBay app on the Mobile Click Sign in Enter Email Click Continue Enter Password Click Sign in | open eBay app in android phone, enter valid email address , password. | User should be able to Sign in and navigate to eBay main page | User should be able to Sign in and navigate to eBay main page | pass
|  | eBay site should be working on the supported devices |  | Go to https://www.ebay.com/ Click Sign in Enter Email Click Continue Enter Password Click Sign in | Go to https://www.ebay.com/, enter valid email address , password. | User should be able to Sign in and navigate to eBay main page | User should be able to Sign in and navigate to eBay main page | pass
TS_Signing in_03 | Verify Sign in with Valid Google Account / Facebook Account Credentials | eBay website should be displayed and sign in page should display continue with google account button | To verify Login with Google Account | Go to https://www.ebay.com/ Click Sign in Click Continue with Google Enter valid gmail id Click Continue Enter valid Password of gmail account Click Create Account | Valid gmail id and Password | User should be able to Login to eBay website | User should be able to Login to eBay website | pass
|  |  |  | Go to https://www.ebay.com/ Click Sign in Click Continue with Google Enter invalid gmail id Click Continue Enter invalid Password of gmail account Click Create Account | invalid gmail id and Password | Display message "gmail id and password that you've entered is incorrect" | Display message "gmail id and password that you've entered is incorrect" | Fail
|  | eBay website should be displayed and sign in page should display continue with facebook account button | To verify Login with Facebook Account | Go to https://www.ebay.com/ Click Sign in Click Continue with Facebook Enter Email or Phone number Enter Password Click Login | Valid Facebook credintials | User should be able to Login to eBay website | User should be able to Login to eBay website | pass
|  |  |  | Go to https://www.ebay.com/ Click Sign in Click Continue with Facebook Enter invalid Email or Phone number Enter invalid Password Click Login | invalid Facebook credintials | Display message "Incorrect Email Address or phone and The password that you've entered is incorrect" | Display message "Incorrect Email Address or phone and The password that you've entered is incorrect" | Fail

## Summary Report
Test summary Report for Sprint1(27-Nov to 02-Dec)
sno | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created user Stories | 15 | 15
2 | Created TestCases | 41 | 39 | 2
3 | No. of tests Executed in Sprint 1,Iteration1 | 41
4 | Defects Reported | 2
5 | No. of Sprints Excuted | 1
Any Challenges
Any BestPractices

## Defect Report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status
EBAY-42 | Sign in as invalid credential | In password option, specific format is not mentioned while registering as a first time user | High | abc@capgemini.com | To do
EBAY-43 | Verify the payment options | User is unable to pay via Google Pay | High | xyz@capgemini.com | To do